## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
[5 empty] | Tursday | Thursday | Tuesday | Thursday | Tuesday | Thursday
User Story #1 | 8
Create a simple GUI - Taabbed Panes (simple GUI) | 7 | Derek |  | 4 | 4 | 4 | 4 | 4 | 4 | 4
One pane will be for modifying the Team Roster | 7.1 | Derek |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
Adding Players to a Roster (simple sql) | 8 | Yousuf |  | 4 | 4 | 4 | 4 | 4 | 4 | 4
Storing player information in the files/database | 8.1 | Yousuf |  | 8 | 6 | 4 | 2 | 1 | 1 | 1
Implementing a lister object that sends new player information to the gui/databse | 5 | Derek |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
Display player information on a roster | 4 | Derek |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
Create UML Diagram | 6 | Michael, Jack, Louis |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Learn how to do basic commands and common practices in mySQL |  | Michael |  | 2 | 2 | 2 | 2 | 2 | 2 | 2
Review how to use common gui patterns, including tabbing |  | Jack, Louis |  | 2 | 2 | 2 | 2 | 2 | 2 | 2
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 |  | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 |  | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 |  | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 |  | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 |  | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 |  | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 |  | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 |  | 0 | 1
TOTAL |  |  |  | 90 | 74 | 72.5 | 47.5 | 35.5 | 16.5 | 33.5 | 14

## TODO Sprint1
Complete Product Backlog | TRUE
Define Sprint Goal | TRUE | `
Comple Burndown Chart | TRUE
Develop UML DIagram | FALSE
Comeplete Spring Retrospective | FALSE
Evaluation | FALSE

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0